Pi

PORTFOLIO INTELLIGENCE

Portfolio Risk Management Module

Risks · Issues · Audits · Impacts — across Project, Program & Portfolio

Product Requirements Document

Pi-PRD-RISK-001  ·  v1.0  ·  June 2026

Prepared by Sycontec Ventures LLP

Confidential — Prepared for Google ODC, Portfolio Controls

# Contents

# 1.  Purpose & Scope

This document specifies the Risk Management module of Pi — a world-class, AI-assisted capability for capturing, discovering, assessing, and acting on risk across the full capital portfolio hierarchy. It originates from the working session with Ali on managing portfolio risk and extends the existing Pi surfaces (Risk Horizon, the Risk Register, and the portfolio heatmap) into a complete, governed module.

Today the portfolio carries risk in scattered, manual forms: regional risk registers maintained as free-text tables in monthly slides, P1/P2 counts surfaced on the Director view, and predicted SLA breaches inferred by the orchestration engine. None of these are connected; none are auditable end-to-end; none roll up cleanly from a single site risk to a portfolio exposure number. Pi closes that gap by treating Risk, Issue, Audit and Impact as first-class, event-sourced entities that exist at every tier and roll up through one consistent model.

The four entities this module manages Risk — something that might happen and would hurt cost, schedule, scope or safety. Forward-looking, probabilistic, owned, mitigated.

Issue — a risk that has materialised, or a problem already live. Reactive, time-bound, resolved through corrective action.

Audit — a structured check that controls are present and working — readiness gates, compliance reviews, data-quality and process audits — producing findings that themselves become risks or issues.

Impact — the quantified consequence (dollars, days, safety, reputation) attached to any of the above, expressed consistently so everything is comparable and roll-uppable.

### In scope

- Manual risk, issue and audit entry — fast capture forms aligned to the register schema already in active ODC use (Site · Risk · Owner · Support Requested · Mitigation · Target Date).

- AI-driven risk discovery — surfacing latent risks from portfolio data (cost/schedule signals, orchestration state, party behaviour, external feeds) using the four condition archetypes.

- Assessment & scoring — a consistent probability × impact model with a normalized 0–100 risk score, mapped to a risk state machine.

- Response strategy — Accept, Mitigate, Transfer, Avoid, plus one-click actions that route into existing workflows and reduce modelled impact.

- Issue management — promotion of a materialised risk to an issue, corrective-action tracking, and resolution.

- Audit workflows — audit templates, scheduling, execution, findings, and finding-to-risk linkage.

- Three-tier roll-up — every entity aggregates Project → Program → Portfolio with heatmaps at each tier.

### Out of scope (this release)

- Source-system risk fields being made writable back into e-Builder or SAP — Pi remains advisory and read-aligned.

- Enterprise GRC certification workflows beyond ODC's portfolio remit.

- Quantitative Monte-Carlo schedule risk simulation (candidate for a later wave).

# 2.  Information Architecture

The module is built on Pi's north-star principle: store events, derive conclusions. A risk is never a static row that gets overwritten; it is a stream of events (raised, scored, mitigated, escalated, materialised, closed) from which every view — register, heatmap, score, narrative — is a projection. This is what makes the audit trail trustworthy and the roll-ups always-consistent.

## 2.1  The three tiers

| Tier | Owner persona | Primary question | Roll-up behaviour |
| --- | --- | --- | --- |
| Portfolio | Director (Brian Smith) | What is my total exposure and where is it concentrated? | Sum of program exposure; top-N risks by score; cross-program themes. |
| Program | Program / Regional Lead | Which projects in my program threaten my commitments? | Sum of project exposure; program-level systemic risks. |
| Project | Project Manager | What could derail this project and what am I doing about it? | Leaf level — risks raised, scored, mitigated against one project. |

Roll-up is computed through the same materialized-path hierarchy Pi already uses (e.g. /portfolio/NA-W/HDL-Hub1-1/), so a portfolio exposure figure is an efficient LIKE aggregation over descendants — no nightly batch, no stale totals.

## 2.2  Canonical entity model

Risk, Issue and Audit-Finding share a common spine so they score, route and roll up identically. The schema below is the generic platform contract; Google-specific values (categories, regions, source systems) are supplied as a configuration pack on top.

risk_entity { entity_id : ULID // immutable, time-sortable kind : RISK ¦ ISSUE ¦ AUDIT_FINDING tier : PROJECT ¦ PROGRAM ¦ PORTFOLIO path : materialized path // /NA-W/HDL-Hub1-1/ title : string category : COST ¦ SCHEDULE ¦ SCOPE ¦ SAFETY ¦ SUPPLY_CHAIN ¦ LEGAL ¦ TECHNICAL ¦ RESOURCE ¦ EXTERNAL ¦ DATA_QUALITY archetype : THRESHOLD ¦ TREND ¦ CORRELATION ¦ ABSENCE source : MANUAL ¦ AI_DISCOVERED ¦ AUDIT ¦ IMPORTED probability : 1-5 (Rare .. Almost Certain) impact_score : 1-5 (Insignificant .. Severe) impact_quant { // the falsifiable consequence dollars : number // standby, rework, escalation days : number // schedule slip safety : enum ¦ null } risk_score : 0-100 (derived; see §5) state : IDENTIFIED ¦ ASSESSED ¦ MITIGATING ¦ ESCALATED ¦ MATERIALISED ¦ RESOLVED ¦ ACCEPTED response : ACCEPT ¦ MITIGATE ¦ TRANSFER ¦ AVOID owner_role : service-role ref // never a raw individual support_requested: string ¦ null // ODC register field mitigation[] : {action, owner_role, due, status, modelled_delta} parties[] : {party_id, role} // vendors / GCs / internal orgs affected_items[] : {type, id, label} // projects, orchestrations evidence[] : {signal, value, source_ref, observed_at} target_date : date event_log[] : append-only, hash-chained // the source of truth links[] : {to_entity_id, rel} // risk->issue, finding->risk }

Why one schema for three things A risk that materialises becomes an issue by appending a MATERIALISED event — not by copying a row. An audit finding that fails becomes a risk by linking, not duplicating. One scoring engine, one heatmap renderer, one roll-up path serves all three. That uniformity is what makes the module feel coherent instead of three bolted-on trackers.

# 3.  Manual Risk & Issue Entry

Fast, low-friction capture is the floor. The form mirrors the register schema already in daily use across ODC regional summaries so adoption requires no relearning — the columns a regional lead types today are the fields Pi captures, plus structured scoring.

## 3.1  Quick-capture form (M-RISK-01)

| Field | Type | Notes / default |
| --- | --- | --- |
| Tier & scope | Selector | Project / Program / Portfolio; defaults to the user's current scope. |
| Title | Text | Verb-first, one line. e.g. “GC tender pricing above guardrail (VLB).” |
| Site / Project | Picker | Resolves to canonical dim_project; campus code chip (VLB, STB, HDL…). |
| Category | Select | Cost / Schedule / Scope / Safety / Supply-chain / Legal / Technical / Resource / External. |
| Identified risk | Long text | The register's free-text description, preserved verbatim. |
| Probability | 1–5 chips | Rare → Almost Certain, with plain-language anchors on hover. |
| Impact | 1–5 chips | Insignificant → Severe; prompts for $ and days quantification. |
| Quantified impact | $ / days | Optional but encouraged; feeds portfolio exposure roll-up. |
| Risk owner | Role picker | Service Role, not an individual (ODC / FeP / ELS as in current registers). |
| Support requested | Text | Mirrors the ODC register column exactly. |
| Mitigation | Repeatable | One or more actions, each with owner-role, due date, status. |
| Target date | Date | Mirrors register; “Ongoing” allowed as an explicit value. |
| Parties involved | Multi-select | From the Party catalogue; defaults to parties on the linked orchestration. |

On submit, the form writes a single RAISED event to the log. Nothing is “saved” as derived state directly; the projection subscriber computes the score, places the risk on the heatmap, and updates the tier roll-ups. A toast confirms: “Risk captured. Now visible on the HDL project heatmap and rolled into NA-W program exposure.”

## 3.2  Issue entry & promotion

An issue can be raised directly (a problem already live) or — more commonly — promoted from an existing risk when it materialises. Promotion preserves the entire history:

- From any risk, the owner selects “Mark as materialised.” Pi appends a MATERIALISED event; the entity's kind becomes ISSUE; the original risk events remain intact and visible.

- Pi pre-fills a corrective-action plan from the risk's existing mitigations, and opens a Workflow Task assigned to the owner Service Role.

- The issue inherits the risk's quantified impact as its starting actual-impact estimate, refined as it is worked.

Continuity by design Because the risk and the issue are the same entity, a portfolio review can always answer “was this foreseen?” — the materialised issue carries its own pre-history. Hidden surprises become rare, and the module reinforces the key-person resilience standard: the record speaks for itself whether or not the person who raised it is in the room.

# 4.  AI-Driven Risk Discovery

Manual entry captures what people already know. The differentiator is surfacing what they don't — latent risks visible in the data but invisible across disconnected systems. Discovery runs on the same engine that powers Pi's Recommendation surface: two generators (a deterministic Rules Engine and the inferential Agent A-305) emit risk candidates that pass through one enrichment pipeline before surfacing.

## 4.1  The four discovery archetypes

Every discovered risk reduces to one of four archetypes. The archetype determines which generator owns it and how it is validated — this is what keeps discovery generic rather than a pile of bespoke rules.

| Archetype | What it detects | Worked example | Generator |
| --- | --- | --- | --- |
| Threshold | A metric crosses a line. | CPI < 0.90 on Henderson Substation → cost-overrun risk auto-raised. | Rules (ECA-native) |
| Trend | N periods of sustained movement. | SPI down 3 weeks running on Pryor Creek → schedule-slip risk. | Rules + windowed state |
| Correlation | Independent signals align. | Mid-East conflict + Europe-sourced LLE + critical-path fitout → supply-chain risk (the Thailand register entry, found before a human writes it). | Agent A-305 |
| Absence | Something expected is missing. | Permit renewal due in 18 days with no orchestration started; GC tender with no bid-levelling task. | Rules (negative-space) + Agent |

Absence is the crown jewel Detecting that something which ought to exist doesn't — a missing backup for a single-filler role, a permit with no orchestration, a change order with no cost review — is where Pi most visibly out-thinks a dashboard. A dashboard can only colour what is in front of it; Pi reasons about the negative space. This is the highest-value and hardest discovery class, and it is unique to the event-sourced model.

## 4.2  Discovery signal sources

A-305 and the Rules Engine draw on the certified semantic layer and Pi's operational core — never raw source tables — plus selected external feeds:

- Earned-value & cost — kpi_earned_value, kpi_cashflow — CPI/SPI deterioration, EAC drift, cashflow variance against the approved plan.

- Orchestration state — SLA pre-breach and breach patterns, stalled stages, the SAP “black-hole” treatment on the approval pipeline.

- Party behaviour — Party Feature Catalogue — supplier reliability decay, SLA-miss-rate jumps, behavioural drift (e.g. Acme Electrical's reliability shift four weeks ago).

- Schedule & field — kpi_field_tasks — RFI aging, submittal backlog, milestone-gate proximity.

- External — Weather, supply-chain indices, regulatory calendars, labour-market signals — the inputs behind correlation-class risks.

## 4.3  From candidate to surfaced risk

Discovered candidates do not appear raw. They pass the same enrichment pipeline Pi uses for recommendations, which guarantees de-duplication, bundling and guard-railing:

GENERATE Rules + A-305 emit risk candidates ¦ (each tagged with archetype + evidence) v NORMALISE resolve cross-system IDs to dim_project DEDUPLICATE collapse candidates sharing dedup_key ¦ (6 SLA trips on one stall -> 1 risk) BUNDLE merge related -> 'systemic supply-chain ¦ risk across 4 EMEA hubs' GATE >=3 corroborating signals for agent risks; ¦ $-impact thresholds route high stakes ¦ to review; reject anything reading raw tables SCORE & RANK probability x impact x confidence (§5) v SURFACE appears on Risk Horizon + register, with a hash-chained reasoning trace a human can audit

Every discovered risk carries a falsifiable predicted impact and a tamper-evident reasoning trace. A reviewer can see exactly which signals fired, accept or reject the risk, and that accept/reject decision becomes a training example in the append-only Outcome Ledger — so discovery precision improves over time on ODC's own portfolio.

# 5.  Assessment & Scoring

Whether a risk is typed in or discovered, it is scored on one consistent model so a $-heavy supply-chain risk and a schedule-slip risk are directly comparable — and roll-uppable.

## 5.1  Probability × Impact

The classic 5×5 matrix gives the qualitative position; the quantified impact gives the money. Both are stored; the matrix drives colour, the dollars drive exposure.

| Probability ↓ / Impact → | 1 Insig. | 2 Minor | 3 Moderate | 4 Major | 5 Severe |
| --- | --- | --- | --- | --- | --- |
| 5 Almost certain | Med | High | High | Critical | Critical |
| 4 Likely | Low | Med | High | High | Critical |
| 3 Possible | Low | Med | Med | High | High |
| 2 Unlikely | Low | Low | Med | Med | High |
| 1 Rare | Low | Low | Low | Med | Med |

## 5.2  The normalized risk score (0–100)

Each entity carries a single composite score so heatmaps, ranking and exposure all read off one number:

risk_score = ( severity_weight * 0.45 ) // P x I matrix band + ( financial_weight * 0.30 ) // $ impact, log-scaled + ( velocity_weight * 0.15 ) // how fast it is worsening + ( proximity_weight * 0.10 ) // nearness of target date scaled to 0-100, then banded: 0-39 Low (green) 40-69 Elevated (amber) 70-89 High (red) 90-100 Critical (deep red, auto-escalates)

Severity comes from the matrix; financial and velocity terms come from the quantified impact and the event log's trajectory; proximity from the target date. Because the score is derived from events, not stored, it recomputes automatically as new signals arrive — a risk that is worsening climbs the heatmap without anyone re-rating it.

## 5.3  Risk state machine

Each entity moves through an explicit lifecycle; every transition is an event with an actor, timestamp and reason.

| State | Meaning | Entry trigger |
| --- | --- | --- |
| Identified | Raised, not yet scored. | Manual submit or AI candidate surfaced. |
| Assessed | Probability, impact and score set. | Scoring complete (manual or auto). |
| Mitigating | Active response in flight. | A response strategy with actions is chosen. |
| Escalated | Raised a tier; needs leadership. | Score ≥ 90, or owner escalates manually. |
| Materialised | Became an issue. | Owner marks materialised; kind → ISSUE. |
| Resolved | Closed; impact avoided or absorbed. | Corrective action complete + verified. |
| Accepted | Consciously tolerated, monitored. | Accept response chosen with rationale. |

# 6.  Response Strategy & Action

Assessment without action is just a prettier register. The heart of the module is deciding how to respond and routing that decision into work that measurably reduces impact — always advisory, always through existing workflows, never committing capital or changing orchestration state directly.

## 6.1  The four responses

| Response | When | What Pi does |
| --- | --- | --- |
| Mitigate | Reduce probability or impact to tolerable. | Opens mitigation actions as Workflow Tasks on Service Roles; each action carries a modelled impact-delta; score recomputes as actions complete. |
| Transfer | Shift the consequence to another party. | Routes to contract / insurance / change-order workflow; links the responsible Party; tracks the transfer instrument. |
| Avoid | Eliminate the risk by changing the plan. | Surfaces the plan change (scope, sequence, sourcing) as a decision needing approval; records the trade-off in the context graph. |
| Accept | Cost of response exceeds the exposure. | Moves to Accepted with a mandatory rationale and a monitoring threshold that re-opens it if signals worsen. |

## 6.2  One-click actions that reduce modelled impact

Every high-scoring risk surfaces the smallest plausible action that materially reduces it, with the expected outcome stated in money and days — the pattern already proven on Risk Horizon:

RISK Monthly Report Assembly likely to breach (~48h, 87%) Mesa Power . Data Stitching . LineSight Expected if no action: $0.4M standby + 2-day schedule slip [ Reassign to Jordan M. ] <- recommended (gold) Expected outcome: SLA risk 87% -> 22%. Avoids $0.4M and 2 days.

Accepting an action never mutates state directly. It creates a Workflow Task assigned to a Service Role (a human or an agent can fill it — they are interchangeable). When the task completes, the Outcome Subscriber measures actual versus predicted impact and writes the result to the ledger, so the module learns which responses actually work on this portfolio.

## 6.3  Aggregate exposure & the weekly triage banner

At portfolio tier, Pi sums the open, quantified exposure into a single headline — “This week's predicted exposure: $2.1M and 7 schedule days” — and ranks risks so leadership triages on consequence, not noise. The same number rolls down: each program and project sees its own slice, reconciling exactly to the portfolio total because they share the materialized-path roll-up.

# 7.  Audit Workflows

Audits are how the module checks that controls are actually present and working — and they are the most powerful source of well-founded risks, because a failed audit finding is a risk with evidence already attached. Pi treats audits as scheduled, templated processes that produce findings, and findings link directly into the risk model.

## 7.1  Audit types

| Audit type | Checks | Cadence |
| --- | --- | --- |
| Readiness gate | Is a project ready to pass a milestone gate (FeP validation, FDOB readiness)? | Per gate |
| Compliance | Permits, AHJ requirements, safety certifications, legal review completeness. | Scheduled + event-driven |
| Financial control | PO/SLA adherence, three-way-match integrity, change-order governance, cashflow-confidence tiering. | Monthly |
| Data-quality | Is the certified data trustworthy? Cross-system ID resolution, stale-tracker detection, manual-stitching exposure. | Continuous |
| Process / SLA | Are orchestrations running to template? Where are governance steps being skipped? | Continuous |
| Supplier | Party performance against contractual SLAs; reliability and behavioural drift. | Quarterly + on-trigger |

## 7.2  Audit lifecycle

Each audit is a process instance with the same orchestration primitives Pi uses everywhere — templates, Service Roles, SLA timers — so audits are themselves auditable.

TEMPLATE reusable checklist of control points, each with a pass/fail criterion + evidence ask ¦ SCHEDULE instance created (cadence or triggered by ¦ an event, e.g. milestone-gate approach) EXECUTE auditor role works the checklist; evidence ¦ captured against each control point FINDINGS each failed/partial point -> a Finding with ¦ severity + recommended remediation LINK Finding -> Risk (or Issue) via links[], ¦ inheriting evidence and quantified impact TRACK remediation = Workflow Tasks on Service Roles; audit closes when findings are dispositioned

Findings are risks with proof A compliance audit that flags “permit renewal not started, due in 18 days” doesn't just log a note — it raises an absence-archetype risk pre-populated with the audit's evidence, scored, and routed for mitigation. The audit trail and the risk trail are one continuous, hash-chained record.

## 7.3  Audit register & findings ledger

| Field | Notes |
| --- | --- |
| Audit ID / type / scope | Tier and dim_project scope; campus chip. |
| Control points | Checklist with pass / partial / fail and evidence reference. |
| Findings | Severity, description, recommended remediation, linked risk/issue ID. |
| Auditor role | Service Role; supports human or agent execution. |
| Status | Scheduled → In progress → Findings raised → Remediating → Closed. |
| Evidence | Immutable, source-referenced; feeds the data-provenance surface. |

# 8.  Heatmaps & Visual Surfaces

The module ships a coherent family of heatmaps and registers that all read off the same scored, event-sourced entities. Colour is always driven by the 0–100 score band (green / amber / red / deep-red), and every cell is a drill-down.

## 8.1  Screen inventory

| Screen | ID | Tier | What it shows |
| --- | --- | --- | --- |
| Portfolio Risk Heatmap | R-01 | Portfolio | Programs × risk categories; cell = aggregate score; top-N exposure; concentration view. |
| Program Risk Heatmap | R-02 | Program | Projects × categories within a program; systemic-risk band across projects. |
| Project Risk Register | R-03 | Project | Full register for one project; the ODC schema, scored and event-sourced. |
| Risk Horizon | S-02 | Portfolio | Forward-looking predicted breaches with $ + day impact (existing, extended). |
| Issue Board | R-04 | All | Materialised issues; corrective-action kanban by state. |
| Audit Console | R-05 | All | Audit schedule, in-flight audits, findings ledger, finding→risk links. |
| Impact Explorer | R-06 | All | Exposure waterfall: total $ and days, decomposed by program / category / driver. |

## 8.2  The portfolio risk heatmap (R-01)

The signature surface. Rows are programs/regions; columns are the risk categories; each cell's colour is the aggregate score of all open risks in that program-category, with the count and dollar exposure inset. It extends the proven Director heatmap pattern from cell-level CPI/SPI to category-level risk.

| Program ↓ / Category → | Cost | Schedule | Supply | Legal | Safety | Exposure |
| --- | --- | --- | --- | --- | --- | --- |
| NA-West | 82 | 74 | 31 | 22 | 45 | $2.1M |
| NA-East | 48 | 55 | 28 | 61 | 19 | $0.9M |
| EMEA | 71 | 40 | 68 | 77 | 24 | $1.4M |
| APAC | 35 | 42 | 79 | 30 | 18 | $0.7M |

Illustrative values. EMEA-Legal (STB AHJ sustainability) and APAC-Supply (Thailand Mid-East conflict) light up exactly the register entries already live in the monthly summaries — demonstrating that Pi structures what ODC teams track today rather than replacing their judgement.

## 8.3  Interaction model

- Click any cell → filtered register of the underlying risks, ranked by score.

- Click a risk → full entity view: event timeline, reasoning trace, mitigations, linked audits/issues.

- Toggle Risk / Issue / Audit-Finding to recolour the same grid by entity kind.

- Toggle score-driver (severity / financial / velocity / proximity) to see what is pushing a cell red.

- Export → board-ready PDF that footnotes the semantic definitions behind every number.

# 9.  Data, Agents & Integration

## 9.1  Semantic bindings

The module reads exclusively from the certified semantic layer and Pi's operational core — never raw source tables.

| Component | Source | Field / model |
| --- | --- | --- |
| Risk counts & severity | kpi_risk (Cortex) | P1/P2 counts, days unresolved, escalation flag, CO pipeline value. |
| Cost / schedule signals | kpi_earned_value | CPI, SPI, EAC vs BAC for threshold & trend discovery. |
| Cashflow risk | kpi_cashflow | Plan vs actual vs forecast variance; confidence tiers. |
| Party-driven risk | Party Feature Catalogue | Reliability, SLA-miss-rate, behavioural drift. |
| Predicted breaches | Orchestration ML / A-305 | Forecast horizon, confidence, factors. |
| Entity state & log | Pi operational core (event store) | Append-only, hash-chained event log per entity. |

## 9.2  Agents

| Agent | Role in this module |
| --- | --- |
| A-305 Recommendation / Discovery | Inferential generator for correlation & absence risks; produces falsifiable predicted impact + reasoning trace. |
| A-211 Cashflow Risk Detector | Threshold/trend detection on cashflow variance against the approved plan. |
| A-203 Key-Person Risk Detector | Absence-archetype risks on single-filler Service Roles; feeds the resilience standard. |
| A-202 Bottleneck Detector | Surfaces process risks from stalled orchestrations and SLA pre-breach. |
| Variance Explainer (A-302) | Attaches the data-vs-human narrative to materialised cost/schedule risks. |

## 9.3  Guardrails (non-negotiable)

- Advisory only — no Pi action commits capital or mutates orchestration state; everything routes into existing workflows.

- ≥3 corroborating signals for any high-stakes agent-discovered risk before it surfaces.

- Financial-impact thresholds route high-dollar risks to approval rather than simple acceptance.

- Every risk carries an immutable, hash-chained reasoning trace; no risk may read raw tables instead of the certified semantic layer.

- Tasks assign to Service Roles, never named individuals — humans and agents are interchangeable fillers.

# 10.  Acceptance Criteria

Binary, testable criteria for the module. Each maps to a UAT case.

| # | Criterion |
| --- | --- |
| 1 | A user can capture a risk at any tier via M-RISK-01 in under 60 seconds; it appears on the relevant heatmap and rolls into program & portfolio exposure within one refresh. |
| 2 | The same entity carries Risk → Issue promotion without data loss; the materialised issue retains the full pre-history. |
| 3 | AI discovery surfaces risks across all four archetypes; each carries ≥3 signals (for agent risks), a falsifiable impact, and an auditable reasoning trace. |
| 4 | Every entity has a normalized 0–100 score that recomputes automatically from new events without manual re-rating. |
| 5 | All four responses (Accept / Mitigate / Transfer / Avoid) are selectable; choosing one opens Workflow Tasks on Service Roles, never on individuals. |
| 6 | Accepting a one-click action creates a task and records predicted impact; on completion the Outcome Subscriber writes actual-vs-predicted to the ledger. |
| 7 | Audits run from templates, produce findings, and a finding links to a scored risk/issue inheriting its evidence. |
| 8 | Portfolio, program and project exposure figures reconcile exactly through the materialized-path roll-up. |
| 9 | All heatmap colours derive from the 0–100 band; every cell drills to the underlying ranked register. |
| 10 | No risk, issue or audit reads raw source tables; all numbers trace to the certified semantic layer with footnoted definitions. |

# 11.  Phasing

| Wave | Delivers |
| --- | --- |
| Wave 1 (in Phase 1) | Manual entry (M-RISK-01), Project Risk Register (R-03), Portfolio & Program heatmaps (R-01/R-02), scoring engine, four responses, Risk Horizon extension. |
| Wave 2 | Full AI discovery across all four archetypes, Issue Board (R-04), Outcome Ledger learning loop, Impact Explorer (R-06). |
| Wave 3 | Audit Console (R-05) with templates and findings ledger, supplier & data-quality audits, finding→risk automation. |

Prepared by Sycontec Ventures LLP  ·  Pi Portfolio Intelligence  ·  Risk Management Module PRD v1.0

Onward.